EBU6304 Software Engineering Group Project

2025-26

| Group number | 2 |  |
| --- | --- | --- |
| member 1 | QM no: 231221386 | Name: JingLun zhou |
| member 2 | QM no: 231221320 | Name: DaWei wang |
| member 3 | QM no: 231221261 | Name: KunPeng lin |
| member 4 | QM no: 231221711 | Name: WuTong yan |
| member 5 | QM no: 231222246 | Name: YanZhen Jiang |
| member 6 | QM no: 231222855 | Name: Xingyu Tao |

First report

- Requirements

1.1 Fact-Finding Techniques

To identify and define the functional and non-functional requirements for the BUPT International School TA Recruitment System, our team adopted three structured fact-finding techniques, aligned with agile software development principles and tailored to the project’s context of replacing the school’s manual Excel/Form-based recruitment workflow. These techniques ensured we captured accurate, stakeholder-centric requirements and validated them for feasibility:

- Desk Research

We analyzed the school’s existing TA recruitment documentation, including Excel spreadsheet templates, application forms, and workflow guidelines. This allowed us to map pain points in the manual process—such as disjointed data storage, lack of real-time application tracking, inefficient applicant screening, and manual workload calculation for TAs. We also cross-referenced the project brief’s basic requirements to ensure alignment with the course’s mandatory technical constraints (Java development, text file storage only, no database integration).

- Stakeholder Requirement Elicitation

We conducted targeted virtual interviews with the three core stakeholder groups of the system: Teaching Assistants (TAs), Module Organisers (MOs), and Academic Administrators (Admins). The interviews focused on capturing role-specific functional needs, usability expectations, and pain points with the current process. For example, MOs highlighted the need for efficient applicant skill review, while TAs requested clear real-time application status updates—all of which were translated into actionable user stories.

- Requirements Validation and Scope Refinement Workshop

Our agile team held an internal workshop to review, validate, and prioritize all collected requirements. We eliminated ambiguous or unfeasible requirements (e.g., database integration, mobile app support) that conflicted with the project’s technical constraints and defined the project scope boundary—excluding non-essential features to keep the design simple, modular, and extensible (per the project brief). All final requirements were documented as SMART (Specific, Measurable, Achievable, Relevant, Time-bound) user stories to guide iterative development.

- 1.2 Iteration Plan

The project is developed using an agile iterative Scrum methodology with four sequential sprints (Iterations 1–4), strictly aligned with the BUPT teaching weeks and official assessment milestones outlined in the project brief (First Assessment: 22nd March 2026; Intermediate Assessment: 12th April 2026; Final Assessment: 24th May 2026). Each iteration has a clear focus, deliverable, and timeline, enabling incremental delivery, continuous feedback, and reflective improvement—core agile principles required for the coursework. All iterations build on the deliverables of the previous one, and lab sessions (scheduled for BUPT Weeks 3,4,5,6,9,10,11,12) are used for project delivery and team reflection.

Iteration 1 (BUPT Week 3: 17th March 2026 – 22nd March 2026)

Focus: Requirements analysis finalization, user story writing, product backlog creation, 3-layer system architecture design, and low/medium-fidelity prototype design for all user interfaces.Deliverables: Finalized product backlog with prioritized user stories, documented system architecture (User Interface Layer, Application Logic Layer, Data Storage Layer), UI prototypes for TA/MO/Admin dashboards, and all deliverables for the First Assessment (30% weight).Rationale: This iteration establishes the project’s foundational design and planning, ensuring the team has a clear roadmap before implementing core functionality—critical for avoiding rework and aligning with agile principles. The iteration concludes on 22nd March to meet the first assessment submission deadline.

Iteration 2 (BUPT Weeks 5–6: 5th April 2026 – 18th April 2026)

Focus: Core functional development (user registration/login for TA/MO, profile management, job posting, job browsing, job application) and implementation of the 3-layer architecture with text file storage (JSON/TXT/CSV).Deliverables: Working Software Version 1.0 with end-to-end core TA recruitment workflow, data storage implemented via users.json, jobs.json, and applications.json, and optimized prototypes for the Intermediate Assessment (20% weight) on 12th April 2026.Rationale: This iteration delivers the Minimum Viable Product (MVP) of the system, addressing all the project brief’s basic requirements. Core features are implemented first to enable the school’s essential TA recruitment workflow, with the 12th April milestone used to demonstrate progress and gather feedback for further refinement.

Iteration 3 (BUPT Weeks 7–8: 22nd April 2026 – 30th April 2026)

Focus: Application management functionality, full Admin feature development (user viewing, application monitoring, TA workload calculation), MO applicant skill review/selection, and system usability improvements.Deliverables: Working Software Version 2.0 with closed-loop recruitment workflow, real-time cross-role data synchronization (TA/MO/Admin), and polished UI/UX for all dashboards.Rationale: This iteration builds on the MVP to add critical management and workflow closure features, addressing all stakeholder needs identified during fact-finding. No formal assessment occurs in this iteration, allowing the team to focus on iterative improvement and bug fixing. A 3-day buffer (19th–21st April) between Iteration 2 and 3 is used for post-assessment reflection and minor bug fixes.

Iteration 4 (BUPT Weeks 9–10: 3rd May 2026 – 10th May 2026)

Focus: System-wide functional testing, bug fixing, performance optimization, final documentation (architecture, user manual, code comments), and demonstration preparation for the final assessment.Deliverables: Polished final Software Version 3.0 with no critical bugs, complete project documentation, and a fully prepared demonstration for the Final Assessment (50% weight) on 24th May 2026.Rationale: This iteration ensures the system is robust, reliable, and well-documented—meeting all the project brief’s final delivery requirements. The extended timeline between Iteration 4 and the final assessment (11th–24th May) is used for final refinements and demo practice.

1.3 Prioritisation Method

To ensure incremental value delivery and alignment with the project’s iterative plan, our team adopted the MoSCoW Prioritisation Framework to categorize all user stories and system features. This framework was selected for its clarity and fit with agile development, and it directly responds to the project brief’s requirement to prioritise features by feasibility and customer needs. All priorities are documented in the product backlog and mapped to the four iterations, with core Must-Have features delivered first to form the system’s MVP. The four priority levels are defined as follows (aligned with the project brief’s basic/extended/AI features):

- Must Have (M/P1): Non-negotiable core features without which the system cannot fulfill the project brief’s basic requirements or support the essential TA recruitment workflow (e.g., TA/MO registration/login, job posting, job application, basic data storage). All Must Have features are delivered in Iteration 2 to meet the intermediate assessment milestone and form the MVP.

- Should Have (S/P2): Important features that enhance the core workflow and address key stakeholder needs, but are not critical to the system’s basic functionality (e.g., MO applicant skill review, Admin user/application viewing, TA application status tracking). All Should Have features are delivered in Iteration 3 to close the recruitment workflow loop.

- Could Have (C/P3): Nice-to-have extensible features that improve usability but are not required for the project’s success (e.g., advanced TA workload sorting, CV preview for MOs, basic AI skill matching). These features are integrated only if time and resources allow, with no impact on core functionality if omitted.

- Won’t Have (W): Features that fall outside the project scope, conflict with mandatory technical constraints (e.g., database integration, Spring Boot framework), or are unfeasible within the project timeline (e.g., mobile app support, complex AI workload balancing). These features are explicitly excluded to keep the design simple and modular, per the project brief’s guidelines.

Key Prioritisation Rationale: We prioritised core user registration and recruitment functions first because they form the foundation of the TA recruitment workflow—all other features (e.g., Admin management, MO screening) rely on these core functions. AI-powered features (e.g., skill matching) were classified as Could Have because they are optional in the project brief and require additional development time, with the core system designed to be extensible for future AI integration if needed.

1.4 Estimation Method

Our 6-person agile team adopted a dual estimation method—person-day time-based estimation (primary) and relative story point estimation (secondary)—to estimate the workload for all user stories and system features. This method was selected for its practicality: person-days provide actionable timelines for task allocation (critical for a small team), while story points enable quick comparison of feature complexity during iteration planning. All estimates are documented in the product backlog, reviewed by the entire team to avoid over/under-estimation, and aligned with the project’s iterative timeline to ensure fair workload distribution.

1.4.1 Person-Day Estimation (Primary)

- Definition: 1 person-day = 1 team member working on a single feature for one full working day.

- Team Allocation: The team is divided into 3 sub-teams (2 members each), assigned to the three core system domains: TA Functionality, MO Functionality, and Admin/System Functionality. This division enables parallel development—maximising efficiency and aligning with the system’s modular 3-layer architecture.

- Estimation Criteria: All estimates are based on three factors: (1) feature complexity (e.g., simple login = 2 person-days, complex workload calculation = 3 person-days); (2) mandatory technical constraints (e.g., JSON file IO, no database integration); (3) the team’s technical proficiency (Java, agile development, file-based storage).

- Governance: Daily 15-minute Scrum standups are held to track progress against estimates. If a feature takes longer than estimated, non-critical Could Have features are deprioritised to ensure the iteration’s core Must Have deliverables are met on time.

1.4.2 Story Point Estimation (Secondary)

- Scale: A simplified 1–3 story point scale (1 = simple, 2 = moderate, 3 = complex) to rank the relative complexity of user stories.

- Use Case: Used during iteration planning to quickly identify high-complexity features (e.g., job application submission = 3 story points) that require cross-sub-team collaboration or additional buffer time. This scale avoids the complexity of larger story point scales (e.g., Fibonacci) and is tailored to the project’s small scope and team size.

Estimation Consistency: All estimates are aligned with the iterative timeline—no single feature is estimated to take more than 5 person-days, and each iteration’s total workload is balanced across the 3 sub-teams to avoid overburdening any group. This ensures the team meets all assessment milestones and delivers incremental value in each sprint.

- Supporting material

2.1 Stakeholder Interview Questions

Teaching Assistant (TA) Interview Questions

- What are the biggest frustrations you experience with the current Excel/Form-based TA application process?

- What key information do you need to see when browsing TA job vacancies for academic modules/school activities (e.g., invigilation)?

- How do you currently track the status of your TA applications, and how could this process be improved?

- What information would you like to include in a digital profile to showcase your skills to Module Organisers?

- Do you have any requirements for uploading and sharing your CV with recruiters?

Module Organiser (MO) Interview Questions

- What is the most time-consuming part of the current TA recruitment process for posting jobs and screening applicants?

- What applicant information (skills, experience, academic background) is most critical for you when selecting a TA for your module?

- How do you currently compare and screen TA applicants, and what digital tools would simplify this process?

- Do you need to export applicant data for internal school records? If so, what format (e.g., CSV/Excel) and information do you require?

- What features would help you efficiently communicate application status updates to TAs?

Academic Administrator (Admin) Interview Questions

- What metrics do you need to monitor to ensure the TA recruitment process runs smoothly and fairly across all modules?

- How do you currently calculate and track TA workload across different modules/activities, and what pain points exist?

- What user management features do you need to oversee the TA recruitment system (e.g., view all users, monitor applications)?

- What data or reports do you require for school-level academic management and TA allocation reporting?

- Do you have any requirements for system access control (e.g., role-based permissions for TA/MO/Admin)?

2.2 Requirements Validation Checklist

A team-internal checklist used to validate all collected requirements against the project brief and agile principles—only requirements that pass all criteria were included in the product backlog:

- Is the requirement specific, unambiguous, and aligned with the project brief’s basic requirements?

- Can the requirement be tested/measured to confirm successful implementation?

- Is the requirement achievable within the project’s timeline and mandatory technical constraints (Java, text file storage only)?

- Is the requirement relevant to the core TA recruitment workflow or a key stakeholder need?

- Can the requirement be delivered within a single project iteration (1–2 weeks)?

- Does the requirement conflict with other core requirements or the project’s scope boundary?

- Is the requirement scalable and compatible with the system’s modular 3-layer architecture?

2.3 Core Requirement Mapping

A high-level map of stakeholder needs to system features (aligned with the project brief’s suggested features):

| Stakeholder | Core Need | Corresponding System Feature |
| --- | --- | --- |
| TA | Create a professional profile | Personal profile management + CV upload |
| TA | Find and apply for suitable TA jobs | Job browsing + job detail viewing + application submission |
| TA | Track application status | Real-time application status updates |
| MO | Post TA job vacancies | Job posting with module/requirement configuration |
| MO | Screen and select suitable TAs | Applicant list viewing + skill review + status marking |
| Admin | Oversee recruitment process | Global application monitoring + user role viewing |
| Admin | Ensure fair TA workload distribution | TA workload calculation and visualization |