## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA001 | TA Account Registration | As a TA, I want to register an account so that I can apply for TA jobs. | P1 | Sprint 2 | 1. TA enters userId, name, email, password to register. | 2 days | Core MVP authentication, aligns with User entity | 2026-03-23 | 2026-03-24
2. System verifies uniqueness of userId/email.
3. Role auto-set to TA.
4. Data saved to users.json via User Service.
TA002 | TA Account Login | As a TA, I want to log into the system so that I can access my account. | P1 | Sprint 2 | 1. Login via email+password with TA role validation. | 2 days | Reuses User Service logic, UI layer integration | 2026-03-25 | 2026-03-26
2. Redirect to TA dashboard on success.
3. Login errors logged to System_Errors.txt.
4. Session status stored locally.
TA003 | Create Personal Profile | As a TA, I want to create a profile so MOs can understand my skills. | P1 | Sprint 2 | 1. TA edits/saves skills, major, contact info. | 3 days | Aligns with User entity's skills attribute | 2026-03-27 | 2026-03-29
2. Profile data real-time updated in users.json.
3. Profile visible only to Module Organisers.
4. Support profile modification.
TA004 | Upload CV | As a TA, I want to upload my CV so that I can show my qualifications. | P1 | Sprint 2 | 1. Support PDF/TXT CV upload (max 10MB). | 3 days | Parallel development with profile feature | 2026-03-27 | 2026-03-29
2. File path stored in cvPath field of users.json.
3. Support CV preview and delete.
4. File IO exception handling.
TA005 | Browse Available Jobs | As a TA, I want to browse jobs so that I can find suitable opportunities. | P1 | Sprint 2 | 1. Job list loaded from jobs.json via Job Service. | 2 days | Core MVP job browsing, aligns with Job entity | 2026-03-30 | 2026-03-31
2. Display title, moduleName, deadline on TA dashboard.
3. Auto-refresh job list on page load.
4. Basic list filtering by module name.
TA006 | View Job Details | As a TA, I want to view job details so that I understand requirements. | P1 | Sprint 2 | 1. Full job details (requiredSkills, description, deadline) displayed. | 2 days | Job detail UI page, pre-requisite for application | 2026-04-01 | 2026-04-02
2. "Apply for Job" button linked to application function.
3. One-click return to job list.
4. Data fetched from jobs.json.
TA007 | Apply for a Job | As a TA, I want to apply for a job so that I can become a TA. | P1 | Sprint 2 | 1. Application record (applicationId, userId, jobId) created. | 3 days | Completes MVP flow: Login→Browse→Apply | 2026-04-03 | 2026-04-05
2. Initial status set to "Pending" in applications.json.
3. Auto-attach profile/CV path to application.
4. Duplicate application blocked.
TA008 | Check Application Status | As a TA, I want to check my status so that I know if I was selected. | P1 | Sprint 3 | 1. Fetch TA's applications from applications.json by userId. | 2 days | Application Service, status tracking feature | 2026-04-16 | 2026-04-17
2. Display status (Pending/Selected/Rejected) with job info.
3. Rejection reason shown if provided.
4. Unread status prompt on dashboard.
MO001 | Post TA Jobs | As a MO, I want to post TA jobs so that I can recruit teaching assistants. | P1 | Sprint 3 | 1. MO inputs jobId, title, moduleName, requiredSkills, deadline. | 3 days | Core MO functionality, aligns with Job entity | 2026-04-06 | 2026-04-08
2. Deadline validation (≥ current date); all fields mandatory.
3. Job data stored in jobs.json via Job Service.
4. Job visible in TA's job list.
MO002 | View Applicants | As a MO, I want to view applicants so that I can evaluate candidates. | P1 | Sprint 3 | 1. Fetch applicants for MO's posted jobs from applications.json. | 3 days | MO applicant management, system expansion | 2026-04-09 | 2026-04-11
2. Link to applicant profile/CV path from users.json.
3. Filter applicants by jobId on MO dashboard.
4. Cross-entity data query implemented.
MO003 | Review Applicant Skills | As a MO, I want to review skills so that I can select suitable candidates. | P2 | Sprint 3 | 1. Compare applicant skills (users.json) with job requiredSkills (jobs.json). | 2 days | Skill review logic, usability improvement | 2026-04-12 | 2026-04-13
2. MO can mark skill match status.
3. Review notes saved locally.
4. UI refinement for skill review panel.
MO004 | Select Applicants | As a MO, I want to select applicants so that I can assign TAs to my module. | P1 | Sprint 3 | 1. MO updates application status to Selected/Rejected in applications.json. | 2 days | Closes recruitment workflow loop | 2026-04-14 | 2026-04-15
2. Status change synced to TA's application page.
3. Over-selection prevented.
4. Rejection reason input supported.
AD001 | View All Users | As an Admin, I want to view all users so that I can manage system users. | P2 | Sprint 3 | 1. Fetch all user records (TA/MO/Admin) from users.json. | 2 days | Admin user management feature | 2026-04-18 | 2026-04-19
2. Filter users by role on Admin dashboard.
3. All user attributes displayed (read-only).
4. Aligns with Admin Service.
AD002 | View All Applications | As an Admin, I want to view all applications so that I can monitor recruitment. | P2 | Sprint 3 | 1. Fetch all application records from applications.json. | 3 days | Admin recruitment monitoring, cross-entity data | 2026-04-20 | 2026-04-22
2. Filter by status, jobId, or userId.
3. Link to associated user/job data.
4. Real-time list refresh.
AD003 | Check TA Workload | As an Admin, I want to check TA workload so that tasks are fairly distributed. | P1 | Sprint 3 | 1. Calculate workload by counting "Selected" applications per TA. | 3 days | Core Admin workload monitoring feature | 2026-04-23 | 2026-04-25
2. Display TA name, module, workload on Admin dashboard.
3. Workload data stored in AD_Workload.json.
4. Basic workload sorting.
SYS001 | Architecture & Prototype | System architecture design and prototype development | P1 | Sprint 1 | 1. Three-layer architecture is designed. | 5 days | Sprint 1 design task | 2026-03-16 | 2026-03-22
2. UI prototypes for all dashboards are completed.
3. JSON file structure is defined.
4. Service boundaries are clarified.
SYS002 | System Testing & Bug Fixing | System test and bug fixing | P1 | Sprint 4 | 1. All user stories are tested. | 4 days | Sprint 4 quality assurance | 2026-04-27 | 2026-04-30
2. JSON data consistency is verified.
3. All identified bugs are fixed.
4. System runs stably.
SYS003 | Final Documentation & Demo | Final documentation and demo preparation | P1 | Sprint 4 | 1. Complete system documentation is finished. | 3 days | Sprint 4 final output | 2026-05-01 | 2026-05-03
2. Demo flow is prepared.
3. System performance is optimised.
4. All deliverables are ready.